## Japan
LOC | Brand | RA Approval Month (Best) | RA Approval Month (Base) | Launch Month (Best) | Launch Month (Base) | Quarter | Year | Status
Japan | Blenrep 100mg vaibhav | May'25 |  | TBC |  | Q3 | 2025 | In Progress
Japan | Gepotidaccin uUTI & GC | TBC |  | TBC |  | Q1 | 2026 | In Progress
Japan | Depemokimab | Jan'26 |  | Apr'26 |  | Q2 | 2026 | In Progress
Japan | Blenrep 70mg | Feb'26 |  | May'26 |  | Q2 | 2026 | In Progress
Japan | Bepirovirsen HBV | Aug'26 |  | Oct'26 |  | Q4 | 2026 | In Progress
Japan | Linerixibat (Lixi) | Dec'26 |  | Mar'27 |  | Q1 | 2027 | In Progress
Japan | CAMLIPIXANT | Sep'27 |  | Nov'27 |  | Q4 | 2027 | In Progress
Japan | B7-H3 | Dec'27 |  | Mar'28 |  | Q1 | 2028 | In Progress

## China
LOC | Brand | RA Approval Month (Best) | RA Approval Month (Base) | Launch Month (Best) | Launch Month (Base) | Quarter | Year | Status
China | APRETUDE (HIV PrEP) Tab & Inj | Apr'24 |  | Jan'25 |  | Q1 | 2025 | Launched
China | Shingrix 18+ |  | 2Q'25 |  | Q4'25 | Q4 | 2025 | In Progress
China | Blenrep (100 & 70) + BorDex | Dec'25 | Jan'26 | Apr'26 | Jun'26 | Q2 | 2026 | In Progress
China | Linerixibat (Lixi) |  | Nov'27 | TBC |  | Q4 | 2026 | In Progress
China | BoosTrix |  | Feb'27 | TBC |  | Q1 | 2027 | In Progress
China | Benlysta SC | 2027 | 2027 | TBC |  | Q2 | 2027 | In Progress
China | Bepirovirsen + SoC | Jan'27 | Mar'27 | Jun'27 | Aug'27 | Q3 | 2027 | In Progress
China | Arexvy (60 years and above) |  | Apr'27 |  | Nov'27 | Q4 | 2027 | In Progress
China | Energix (Relaunch) |  | Apr'25 |  | Apr'26 | Q2 | 2026 | In Progress
China | Depemokimab | Apr'26 | Jun'26 | Oct'26 | Jan'27 | Q1 | 2027 | In Progress

## Canada
LOC | Brand | RA Approval Month (Best) | RA Approval Month (Base) | Launch Month (Best) | Launch Month (Base) | Quarter | Year | Status
Canada | Omjjara | Nov'24 |  | Jan'25 |  | Q1 | 2025 | Launched
Canada | Blenrep | Jul'25 |  | Aug'25 |  | Q3 | 2025 | Launched
Canada | Depemokimab | Feb'26 |  | Q2'26 |  | Q2 | 2026 | In Progress
Canada | Linerixibat (Lixi) | Q2'26 |  | Q2'26 |  | Q2 | 2026 | In Progress

## AUSTRALIA & Viiv
LOC | Brand | RA Approval Month (Best) | RA Approval Month (Base) | Launch Month (Best) | Launch Month (Base) | Quarter | Year | Status
Australia & Viiv | Omjjara | Dec'24 |  | Apr'25 (Reimbursement) |  | Q2 | 2025 | Launched
Australia & Viiv | Blenrep | Nov'25 |  | Aug'26 | Dec'26 Base (Reimbursement) | Q4 | 2025 | In Progress
Australia & Viiv | Depemokimab | May'26 |  | Aug'26 (Reimbursement) |  | Q3 | 2026 | In Progress
Australia & Viiv | Nucala COPD | Mar'26 |  | Dec'26 | Apr'27 | Q4 | 2026 | In Progress
Australia & Viiv | Gepotidacin uUTI | Jun'26 |  | Jan'27 (Reimbursement) |  | Q1 | 2027 | In Progress
Australia & Viiv | Bepivirosen | May'27 |  | Aug'27 |  | Q3 | 2027 | In Progress
Australia & Viiv | Ventolin LCV | Jan'27 |  | Jan'28 (TBC) |  | Q1 | 2028 | In Progress

## Korea
LOC | Brand | RA Approval Month (Best) | RA Approval Month (Base) | Launch Month (Best) | Launch Month (Base) | Quarter | Year | Status
Korea | Omjjara (Private Launch) | Sep'24 |  | Mar'25 |  | Q1 | 2025 | Launched
Korea | Vocabria + Rekambys | Mar'22 |  | Apr'25 | May'25 | Q2 | 2025 | Launched
Korea | Nucala (AI) | Mar'25 |  | Apr'25 | May'25 | Q4 | 2025 | In Progress
Korea | Omjjara (Reimbursement) | Sep'24 |  | Jan'26 |  | Q2 | 2026 | In Progress
Korea | Blenrep (Reimbursement) | Dec'25 | Feb'26 | Aug'28 |  | Q3 | 2028 | In Progress
Korea | Arexy | Dec'24 |  | May'25 |  | Q2 | 2025 | Launched
Korea | Fluarix | Apr'25 |  | Sep'25 |  | Q3 | 2025 | In Progress
Korea | Nucala (AI Reimbursement SEA) | Mar'25 |  | Dec'25 |  | Q4 | 2025 | In Progress
Korea | Blenrep (Private Launch) | Dec'25 | Feb'26 | Mar'26 | Apr'26 | Q2 | 2026 | In Progress
Korea | Bepivirosen | Jun'27 |  | Jan'28 |  | Q1 | 2028 | In Progress
Korea | Bepivirosen (Reimbursement) | Jun'27 |  | Dec'28 |  | Q4 | 2028 | In Progress

## Taiwan
LOC | Brand | RA Approval Month (Best) | RA Approval Month (Base) | Launch Month (Best) | Launch Month (Base) | Quarter | Year | Status
Taiwan | Apretude | Jan'25 |  | Jan'26 Launch/Reimbursement |  | Q1 | 2026 | In Progress
Taiwan | Omjjara (self Pay) | Feb'25 |  | Jun'25 |  | Q3 | 2025 | Launched
Taiwan | Fluarix | Mar'25 |  | Sep'25 |  | Q3 | 2025 | In Progress
Taiwan | Omjjara (Rem) | Feb'25 |  | Oct'25 |  | Q4 | 2025 | In Progress
Taiwan | Nucala (SS) | Jun'21 |  |  | Jan'26 Reimbursement | Q1 | 2026 | In Progress
Taiwan | Blenrep (100 & 70 mg) | Mar'26 |  | Jul'26 |  | Q3 | 2026 | In Progress
Taiwan | Blenrep (Remibursement) | Mar'26 |  | May'27 |  | Q2 | 2027 | In Progress
Taiwan | Bepivirosen | Jan'27 |  | Apr'27 |  | Q2 | 2027 | In Progress
Taiwan | Bepivirosen Reimbursement | Jan'27 |  | Jan'28 |  | Q1 | 2028 | In Progress
Taiwan | Jampeli | Apr'26 |  |  | Aug'26 | Q3 | 2026 | In Progress
Taiwan | Jampeli Reimbursement | Apr'26 |  | Jan'27 |  | Q1 | 2027 | In Progress
Taiwan | Depemokimab (AI & SS) | Dec'26 |  | Apr'27 | May'27 (Reimbursement) | Q2 | 2027 | In Progress

## Hong Kong
LOC | Brand | RA Approval Month (Best) | RA Approval Month (Base) | Launch Month (Best) | Launch Month (Base) | Quarter | Year | Status
Hong Kong | Omjjara | Dec'24 |  | May'25 |  | Q2 | 2025 | Launched
Hong Kong | Blenrep | Oct'25 | Dec'25 | Jan'26 | Mar'26 | Q1 | 2026 | In Progress
Hong Kong | Nucala (COPD) | Apr'26 |  | TBC |  | Q3 | 2027 | In Progress
Hong Kong | Depemokimab | Aug'26 | Oct'26 | Sep'26 | Jan'27 | Q4 | 2026 | In Progress
Hong Kong | Bepirovirsen | May'27 | Oct'27 | Jul'27 | Dec'27 | Q3 | 2027 | In Progress
Hong Kong | Ventolin (RCV) | TBC |  | TBC |  | Q2 | 2028 | In Progress

## Singapore
LOC | Brand | RA Approval Month (Best) | RA Approval Month (Base) | Launch Month (Best) | Launch Month (Base) | Quarter | Year | Status
Singapore | Omjjara | Nov'24 |  | Mar'25 |  | Q1 | 2025 | Launched
Singapore | Blenrep | Jun'26 | Sep/Nov'26 | Jul'26 | Jan/Mar'26 | Q3 | 2026 | In Progress
Singapore | Depemokimab | Q4'2026 | Jan'27 | Q1'27 | Dec'27 | Q1 | 2027 | In Progress
Singapore | Ventolin (RCV) | Sep'27 (TBC) |  | Oct'27 (TBC) |  | Q3 | 2027 | In Progress

## Newzealand
LOC | Brand | RA Approval Month (Best) | RA Approval Month (Base) | Launch Month (Best) | Launch Month (Base) | Quarter | Year | Status
Newzealand | Zezula | Jul'25 |  | Q4'25 |  | Q4 | 2025 | In Progress
Newzealand | Trelegy (200) | Jun'22 |  | Q1'26 |  | Q1 | 2026 | In Progress
Newzealand | Jamperli | Jan'26 |  | 2026 |  | Q3 | 2026 | In Progress
Newzealand | Omjjara | Mar'25 |  | Feb'27 | Feb'27 | Q1 | 2027 | In Progress
Newzealand | Ventolin (LCV) | TBC |  | Apr'27 |  | Q2 | 2027 | In Progress
Newzealand | Benlysta (Pen) | Q2'27 |  | 2027 |  | Q3 | 2027 | In Progress
Newzealand | Blenrep | Jul'26 |  | 2027 |  | Q4 | 2027 | In Progress
Newzealand | Depemokimab | Jul'27 |  | Q4'27 |  | Q1 | 2027 | In Progress
Newzealand | Cabenuva | 2026 |  | Q2'28 |  | Q4 | 2027 | In Progress